## Sheet1
The Brighter Side of Things
Gant chart
Activity | Resource | Time Est. | January 29th | Feb. 5 - 20 | Feb. 25 - March 9 | March 9 - 19 | March 30 - April 8
Meet with InSource | Jordan | 1 days
Design main page and directional buttons | Jordan | 15 days
Create working web pages for the legal section | Jordan | 11 days
Create working web pages for the P/A section | Jordan | 10 days
Finalize site and functions and notebook for competition | Jordan | 9 days